## Intro
Primavera P6 Web vs P6 Professional vs Primavera Cloud Functionality Matrix
This document provides an outline of functionality included in P6 EPPM Web. Included is a comparison of the functionality provided in P6 Professional when run as a standalone application and not part of the larger enterprise application. The introduction of Primavera Cloud and it's wider scope and architecture makes for a more challenging comparison, but its provided here with best endeavours. For example, workspaces are very different from EPS functionality but are the closest comparison objects.
Versions Compared
P6 EPPM v19.12
P6 Professional v19.12
Primavera Cloud v20.8
Links to related sections:
User
Mobile
Dashboards
Workspaces
Portfolios
Programs
Projects
Resources
Administration
Reports
Ideas
Legend: P Feature fully supported
Legend: P Feature supported with less capability

## User
User Specific
Feature |  | P6 EPPM Team Member | P6 EPPM Client Functionality | P6 Professional Functionality | Primavera Cloud | Notes
General
| Opens application in previous location |  |  |  | P
| Default Landing Page (user preference) | P
| Getting Started Page with Typical Tasks |  |  |  | P
| Global Search across all objects |  |  |  | P
Timesheets / Status Updates
| Activity Timesheets | P |  |  | P
| Supervisor Timesheets |  |  |  | P
| Approve/reject Timesheets | P |  |  | P
| Overhead Types | P |  |  | P | OPC has Hour Types which is similar to Overhead Codes.
| Timesheet approval options | P |  |  |  | P6 supports auto-approval, 1 level of approval, or 2 levels of approval. OPC supports only 1 level.
| My Activities | P |  |  | P | Equivalent functionality between browser version of Team Member and Primavera Cloud My Activities on user app.
| Status Update Approvals | P |  |  |  | Planned for 2022 in OPC.
Other
| Task Inbox & Email Notifications |  |  |  | P | Workflow tasks sent to recipients, cloud background tasks, discussion threads etc.
| User Preferences | P | P | P | P
| Proxy to/from users |  |  |  | P
| News Feed |  |  |  | P | User subscription to updates
| Monitor Workflows |  |  |  | P
| Manage Services | P |  |  | P

## Mobile
User Specific
Feature |  | P6 EPPM Team Member | P6 EPPM Client Functionality | P6 Professional Functionality | Primavera Cloud | Notes
Common Features
| Discussion threads |  |  |  | P | Supported on tasks and activities
| Location Services on mobile device | P
| Offline Usage | P |  |  | P | Excludes discussion threads
| View project files/documents |  |  |  | P
Activity Progressing
| Update your assigned activities | P |  |  | P | Includes progressing resource assignments for your activity
| Update your resource assignments | P |  |  | P
| Custom activity/assignment filters | P |  |  |  | This is the scenario in P6 where web-defined filters are defined to drive what shows on mobile
| View/edit codes and confgured fields | P |  |  | P
| Filter by codes and configured fields | P |  |  |  | Planned for summer 2022
| View Files/documents attached to activities | P |  |  | P
| Attach files, photos, and videos | P |  |  | P | Only supported on iOS
| Markup photos,documents | P |  |  | P | Only supported on iOS
Tasks
| Task Analysis |  |  |  | P | Subset of views/charts available on web
| Work Plan - Edit & Review |  |  |  | P | Only supports fixed data window (last week, this week, next week)
| View/edit codes and confgured fields |  |  |  | P
| Filter by codes and configured fields |  |  |  |  | Planned for summer 2022
| Task Constraints |  |  |  | P
| Task Hand-offs |  |  |  | P
Timesheets |  | P

## Workspace EPS
Workspaces
Feature |  | P6 EPPM Web Functionality | P6 EPPM Client Functionality | P6 Professional Functionality | Primavera Cloud | Notes
EPS / Workspaces | [5 empty] | In this section we compare the EPS in P6 with Workspaces in Primavera Cloud. They are very different in scope but closest thing to compare.
| Configuration Stored per EPS/Workspace |  |  |  | P
| Template Dictionaries per EPS/Workspace |  |  |  | P
| Defaults, Rules, Metadata per EPS/Workspace |  |  |  | P
| Scorecard View | P | Project View
| Confgurable Columns | P | P | P
| Gantt View | P | P | P | P | In Primavera Cloud, currently provided as a Chart in Workspace or Portfolio Dashboard, but not as configurable as EPS Gantt summary in P6.
Strategies
| Define Strategy Hierarchy |  |  |  | P
| Strategy Scorecard |  |  |  | P
| Assign Projects, Weighting & Scorecards |  |  |  | P
| Assign & Track Measures |  |  |  | P
| Assign Codes and Values |  |  |  | P
| Attach files |  |  |  | P
Create, Import/Export
| Create Template projects | P |  |  | P
| Import/Export XML | P | P | P | P
| Granular control over data during XML import | P | P | P | P | P6 has advanced options, OPC does not.
| Import/Export Baselines with XML | P | P | P | P | Limit of 3 baselines when importing P6 XML files into OPC.
| UN/CEFACT XML Data Export | P | P | P
| Link P6 Project to Contract Management | P | P | P
| Link P6 Project to Primavera Unifier | P | P
| Link P6 Project to Primavera Cloud |  |  |  | P
| Configure Primavera Analytics settings | P
| Configure Mobile Progress settings | P |  |  | P
| Configure Publication Services | P
| Import/Export XER |  | P | P |  | Planned for 2022 in OPC.
| Import/Export P3 |  | P | P
| Import/Export XLS |  | P | P | P | Dependent on subject area or page to be imported/exported in OPC. Many pages in OPC support XLS import.
| Check In/Check Out |  | P | P
| Ability to see who is currently in the project | P | P | P
| Send Project |  | P | P
Other
| Define File/Document Repository Templates |  |  |  | P
| Add files/Include Document Templates |  |  |  | P

## Portfolios
Projects
Feature |  | P6 EPPM Web Functionality | P6 EPPM Client Functionality | P6 Professional Functionality | Primavera Cloud | Notes
Manage Portfolios
| Manual Creation | P | P | P | P | Used only for opening projects in P6 Professional
| By Filter | P |  |  | P
| Scheduled Automation |  |  |  | P
Portfolios
| Home Page |  |  |  | P
| Contains Programs |  |  |  | P | as well as Projects
| Contains Portfolios |  |  |  | P
| Snapshots |  |  |  | P | Point in time saving of data for comparison
| Funding sources |  |  |  | P
| File/Document Repository |  |  |  | P | inc. Template definition of folder structure and template files
Manage Portfolio Views
| Prioritization Matrix |  |  |  | P | Multi project view of project evaluations. Editable, if required.
| Measures Tracking |  |  |  | P | Periodic Target vs Actual Tracking. Typically covers fiscal and non fiscal benefits
| Sparklines on Measures |  |  |  | P
| Investor Maps / Bubble Charts | P |  |  | P | Greater flexibility in Primavera Cloud inc. Ref lines for background colour thresholds
| Histograms | P | P | P | P | Tracking View in P6 Professional. Dashboard charts in Primavera Cloud and Budget and Resource Planning Views
| Pie Charts | P |  |  | P | Dashboard charts for the Portfolio in Primavera Cloud
| Scorecards | P |  |  | P
| Side-by-Side Histogram | P |  |  | P
| Stacked Histogram | P | P | P | P | Tracking View in P6 Professional
| Trend Charts |  |  |  | P | Comparison against historical data periodically
| Spending Plan |  |  |  | P | Drillable annual breakdown of budget, forecast, actual, approved for portfolio.
Budget Planning
| Manage Multiple Scenarios |  |  |  | P
| Configurable Planning Sheet |  |  |  | P
| Approval Workflows |  |  |  | P
| Target Budget per Scenario |  |  |  | P
| Manual Selections of projects | P |  |  | P
| Scenario Optimization - Efficient Frontier |  |  |  | P
| Scenario Optimization - Waterline | P |  |  | P
| Link/unlink project budget/forecast |  |  |  | P
| Unmet dependencies |  |  |  | P
| Spending Plan per Scenario |  |  |  | P
| Scenario Comparison |  |  |  | P | side by side comparison of multiple scenarios for each planning year
| Funding Allocation & analysis |  |  |  | P
Resource Planning
| Manage Multiple Scenarios |  |  |  | P
| Configurable Planning Sheet | P |  |  | P
| FTE's or Hours |  |  |  | P
| Approval Workflows |  |  |  | P
| Allocations Gantt | P |  |  | P
| Role Graph Analysis per scenario | P |  |  | P | Stacked or Side by Side view of Demand, Allocations, Commitments by Project or other grouping. Role selections
| Manual Selections of projects | P |  |  | P
| Scenario Optimization - Efficient Frontier |  |  |  | P
| Scenario Comparison |  |  |  | P | side by side comparison of multiple scenarios for each planning year
Capacity Planning |  | P | Tracking View | Tracking View |  | Capacity plan displays a gantt chart and role based profile/spreadsheet. Tracking View can display a gantt chart and resource profile/spreadsheet.
Performance Status |  | P | Project View | Project View |  | P6 Web offers a consolidated view of project performance within a portfolio. Performance status columns can be displayed in the Project View of P6 Pro
Gantt Chart |  | P | Partial - Project View | Partial -Project View |  | P6 Web Portfolio Gantt Chart displays a project level summary gantt and project units or costs in a spreadsheet/histogram. Project View displays project level summary gantt.
ROI |  | P |  |  | P

## Programs
Projects
Feature |  | P6 EPPM Web Functionality | P6 EPPM Client Functionality | P6 Professional Functionality | Primavera Cloud | Notes
Schedule | [5 empty] | P6 does not support Programs, but one or more projects can be opened at any time.
| Program Milestones & Summary View | P | P | P | P | In OPC this is a Standard view available on the Activities page in a program.
| Consolidated multi project schedule | P | P | P | P
| Inter-project dependencies | P | P | P | P
| Tracking Gantt |  | P | P
| Configurable Summary Bars |  | P | P
| Program Role/Resource Usage |  | P | P | P | Using Tracking Gantt in P6 Client
Resources/Roles
| Resource Assignment Analysis | P | P | P | P | Configurable Periods, Grouping, Values (Units, Costs), Columns etc.
| Role/Resource Analysis | P | P | P | P | Configurable Periods, Grouping, Staffed vs Unstaffed, Utilisation, Stacked by Project etc.
Costs
| Summary Cost Sheet by CBS Code |  |  |  | P
| Summary Cost Sheet by Cost Category |  |  |  | P
| Summary Cost Sheet by Project | P | P | P | P
| Program Cashflow |  |  |  | P
| Tracking Gantt - Cost Profiles |  | P | P
| Program Funds |  |  |  | P
| Program Budget (top down) |  |  |  | P
Risk
| Risk adjusted program schedule |  |  |  | P
| Program specific Risks |  |  |  | P | Including impacts, probability, responses etc.
| Program Risk Register | P |  | P | P | Aggregated project risks (plus in Primavera Cloud's case additional Program Risks)
| Program Risk Matrix & Thresholds |  |  |  | P
Lean Tasks
| Task List, Configured Views |  |  |  | P | Aggregated task list across program
| Create/Plan Tasks |  |  |  | P
| Hand-Offs |  |  |  | P
| Commit Tasks and Progress Tasks |  |  |  | P
| Print Saved Views of Program Tasks |  |  |  | P
Strategic Alignment
| Evaluation Matrix |  |  |  | P
Other
| File/Document Registry |  |  |  | P
| Program Dashboards |  |  |  | P
| Custom Logs |  |  |  | P | Typically used to for recording multiple records against the project, such as Lessons Learned Log. Multiple logs or registers can be defined, each for recording multiple records.

## Projects
Projects
Feature |  | P6 EPPM Web Functionality | P6 EPPM Client Functionality | P6 Professional Functionality | Primavera Cloud | Notes
General
| Project Home Page / Summary |  |  |  | P | Primavera Cloud takes a different approach by providing a home page for each object in the system.
| Configurable Project Details Form |  |  |  | P
| Forms - Configurable/meta data updates |  |  |  | P | Form templates for easy project updates outside of workflows
| Project Scheduled Services | P | Job Services | Job Services | Manage Services | Primavera Cloud runs all services as background services and where relevant include scheduled runs, such as reports, notifications
Project Team
| Companies & Company Details |  |  |  | P | Companies utilised on the project (mainly used in Lean capapbility)
| Project Users, User Groups & Security Permissions | P | P | P | P
Strategic Alignment
| Strategies & Project Contribution |  |  |  | P
| Evaluation Matrix |  |  |  | P
WBS Dictionary
| WBS page |  | P | P | P | P6 Web provides most functions through the activity gantt view
| Add WBS from Template/other project |  | P | P | P
| Copy/paste | P | P | P | P
| Saved Views, Many aggregated columns e.g. schedule % complete | N/A | P |  | P | View changes are saved per user on the WBS page in OPC. It is planned to add more columns and activity rollups to the WBS page in the future, and then saved views will be added.
| Permissions by WBS | P | P
| Tabular or Chart View - Configurable | P | P | P |  | P6 Web and Primavera Cloud provide just Tabular View
| Top Down WBS & Bottom up aggregated Budgets | P | P | P |  | OPC provides top-down budgets at the project level, as well as bottom up budgets aggregated to the WBS on the Activities page.
| WBS Milestones - high level progress | P | P |  |  | Planned for late 2023/early 2024.
| WP's & Docs | P | P | P | P | File attachments in OPC.
| Earned Value & ETC calculation rules by WBS | P | P |  |  | Planned for late 2023/early 2024.
| WBS Codes & UDF's | P | P | P | P | Greater functionality with codes and formula based UDF's in Primavera Cloud
Activities
| Activity View | P | P | P | P
| Layouts | Grid, Gantt, Network | Grid, Gantt, Network | Grid, Gantt, Network | Grid, Gantt, Network | OPC only renders Activity Network for schedules with less than 6K activities currently.
| Configurable Columns, Grouping and Filtering | P | P | P | P
| Quick search for columns | P |  |  | P
| Filtered activity search/find | P |  |  | P
| Multiple Column Sorting | P | P | P | P
| Easy access column functions e.g. sort, group, width | P |  |  | P
| Pin Columns i.e. scrollable or not | P |  |  | P
| Combined Relationship Detail Panel | P | P | P | P
| Relationship slide-out panel |  |  |  | P
| Replace relationship assignment (not remove, then add) | P | P | P | P
| Display Activity or Resource Spreadsheet/Histogram as bottom layout |  | P | P | P
| Display resource allocation when assigning resources to tasks | P |  |  | P
| Manage WBS in Activities view | P |  |  |  | On OPC roadmap.
| Reorganize Now |  | P | P | P
| Renumber Activity IDs |  | P | P | P
| Fill Down | P | P | P | P
| Link Activities | P | P | P | P
| Open Dependent Projects | P |  |  | P | For Primavera Cloud, delivered more through Programs functionality
| Risk Analysis Results in Gantt chart |  |  |  | P | Use Optimistic, Pessimistic or P50 dates for bars
| Customize Endpoints, Patterns, Label Positions, etc. |  | P | P |  | P6 Web and Primavera Cloud use Themes to apply formatting. More options for shape endpoints and patterns in P6 Professional
| Apply filter to bars |  | P | P
| User defined bars | P | P | P | P | All date fields available in Primavera Cloud for user bars.
| Color coded bars by activity code | P |  |  | P
| Collapsed Bar Formatting |  | P | P |  | On OPC roadmap.
| Configurable Progress Bar |  | P | P | P
| Timescale - Hour and Shift, Three Line, Ordinal |  | P | P |  | Hourly and ordinal timescale on OPC roadmap.
| Shrink Vertical Grouping Bands |  | P | P
| Activity Network Boxes - Make editable, configure box positions | P | P | P | P
| Set and display Tertiary BL in Activities View |  | P | P | P
| Update Progress |  | P | P |  | Automated calculation of progress
| Data Date Progress Options i.e. Jagged timenow |  | P | P
| Configurable Sight Lines | P | P | P | P | Switch on/off in P6 Web and Primavera Cloud
| For Review activity field |  | P | P
| Undo |  | P | P | P
| Activity Types | Activity/Resource Depndent, Start/Finish Milestone, LOE, WBS Summary | Activity/Resource Depndent, Start/Finish Milestone, LOE, WBS Summary | Activity/Resource Depndent, Start/Finish Milestone, LOE, WBS Summary | Activity/Resource Depndent, Start/Finish Milestone, LOE | WBS Summary activity type planned for OPC in 2022.
| Duration Types | P | P | P | P | Fixed Units/Time, Fixed Units, Fixed Duration & Units, Fixed Duration & Units/Time
| Percent Complete Type | Physical, Duration, Units | Physical, Duration, Units | Physical, Duration, Units | Physical, Duration, Units, Scope
| Primary & Secondary Constraints | P | P | P | P | 9 matching types
| Discussion Threads | P |  |  | P
| Notebooks | P | P | P |  | Notebooks or something equivalent on OPC roadmap for 2022..
| Activity Codes | P | P | P | P
| UDF's, Configured Fields | P | P | P | P | Greater functionality with codes and formula based UDF's in Primavera Cloud
| Trace Logic | P | P | P | P | OPC only renders Trace Logic for schedules with fewer than 6K activities currently.
| Tasks, Task Status & Indicators on Activities | P | P | P | P | More task fields provided in Prim Cloud e.g. Company, Pred Count, Succ Count, Flags
| Steps | P | P | P |  | Steps in Primavera Cloud can be represented by tasks, but assuming here that steps and tasks are used for different purposes. It is on the roadmap to be able to leverage tasks to manage steps in the future in OPC.
| Scope Assignments |  |  |  | P
| Assign Codes, Risks, Predecessors and Successors to Multiple activities |  | P | P | P
| Global Update | P | P | P | P | Global Change definitions are per project in OPC, global in P6.
| Schedule Comparison | P |  |  | P | Separate product in P6, built into OPC.
| Line numbers |  | P | P | P | Available in print output only in OPC.
| Import/Export to/from Excel | P | P | P | P
| Import WBS/Activities from another template or project | P |  |  | P
Scheduling
| Ignore/include external relationships | P | P | P | P
| Make open ended activities critical | P | P | P | P
| Use Expected Finish Dates | P | P | P | P
| Level Resources during scheduling | P | P | P
| Recalculate assignment costs after scheduling | P | P | P | P
| Scheduling of progressed activity options | Retained Logic, Progress Overrride, Actual Dates | Retained Logic, Progress Overrride, Actual Dates | Retained Logic, Progress Overrride, Actual Dates | Retained Logic, Progress Overrride, Actual Dates
| Calculate Start to Start Lag from | ES, AS | ES, AS | ES, AS | ES, AS
| Critical based on | Total Float Value, Longest Path | Total Float Value, Longest Path | Total Float Value, Longest Path | Total Float Value, Longest Path
| Total Float Calculation | LS-ES, LF-EF, Smallest of SF, FF | LS-ES, LF-EF, Smallest of SF, FF | LS-ES, LF-EF, Smallest of SF, FF | LS-ES, LF-EF, Smallest of SF, FF
| Calculate Float based on | Each Project, Opened Projects | Each Project, Opened Projects | Each Project, Opened Projects | Each Project, Opened Projects
| Calendar for Relationship Lag | Pred Cal, Succ Cal, 24 Hr, Project Default | Pred Cal, Succ Cal, 24 Hr, Project Default | Pred Cal, Succ Cal, 24 Hr, Project Default | Pred Cal, Succ Cal, 24 Hr, Project Default
| Multiple Float Paths, No of Paths | P | P | P | P
| Multiple Float Path Method | TF, FF | TF, FF | TF, FF | TF, FF
Schedule Quality
| Schedule Check Report | P |  |  | P | Schedule Health panel in OPC.
| Interactive Schedule Health scorecard with drill down |  |  |  | P
| Project Schedule Health Score (for Portfolio Reporting) |  |  |  | P | Includes weighting on each active check for scoring
| Configurable tolerances/targets | P | P | P | P
| Editable descriptions of checks |  |  |  | P
Baselines & Scenarios
| Define Baselines | P | P | P | P | Unlimited Baselines in OPC
| Edit Baselines | P |  |  | P | Baselines are part of the same project as the current schedule in OPC, and can be opened directly on the Activities page. In P6, baselines are stored as separate projects in the DB and must be restored as regular projects in order to edit them.
| Configurable Baseline Types | P | P | P | Original, Current, Supplementary | On roadmap to support Baseline Types in OPC.
| No of user assigned baselines | 3 | 3 | 3 | 3
| No of baselines choices for gantt | Project, User | Project, Primary, Secondary, Tertiary | Project, Primary, Secondary, Tertiary | Original,Current,Supplementary,User1,User2,User3
| Auto add missing activities to baseline from current |  |  |  | P
| Revert Baseline Changes |  |  |  | P
| Create a baseline in the past |  |  |  | P | A baseline can be created that represents any point in time up until the date the project was created.
| Define Scenario Schedule |  |  |  | P
| Edit Scenarios |  |  |  | P
| Set Scenario or Baseline to Current Schedule |  |  |  | P
| Reflection Projects |  | P | P |  | Planned for 2022.
Schedule Comparison
| Project Differences Report |  | P | P |  | Planned for 2022 as a download to Excel report.
| Interactive Analysis with Scorecard, Gantt, Drill down |  |  |  | P
| Point in time comparison (as well as scenarios, baselines etc.) |  |  |  | P
| Saved Views/Layouts |  |  |  | P
| Easy focus on variances |  |  |  | P
Printing
| Print Preview based on Screen choices/setup | P | P | P | P
| Configurable print options per saved view |  |  |  | P
| Configure header, footer, content at print run time | P | P | P | P | Options saved per layout in P6 or Saved View in Primavera Cloud. Not the same flexibility in P6 Web
Resource & Bottom Up Cost Planning
| Role and Resource Assignments | P | P | P | P
| Replace Resource Assignments |  |  | P | P
| Assign Resource by Role |  | P | P |  | On longer term OPC roadmap
| Expense Assignments | P | P | P |  | Planned for late 2022/early 2023.
| Add Activity Costs without resource assignment |  |  |  | P
| Non unit rate driven costs |  |  |  | P
| Rate Type on Assignments | P | P | P | P
| Use of Curves, Lags, Units/Time | P | P | P | P
| Staff Role | P |  |  | P
| Assign Role/Resource to multiple activities | P | P | P | P
| Utilisation Chart on Assigning Resource or Role | P |  |  | P
| Configurable Utilisation Chart on Assignments | P |  |  |  | Choice of all projects or selected project(s), time period, units or costs
Project Resource/role Usage
| Bottom layout Resource & Role Costs Histogram/spreadsheet |  | P | P | P
| Group assignments in spreadsheet |  | P | P |  | On OPC roadmap.
| Role and Resource selection |  | P | P | P
| Stacked by Resource Groups |  | P | P | P | In P6, the groups are created manually based on filters. In Primavera Cloud you can use resource codes values to represent the stack.
| Show All Projects |  | P | P
| Periodic Bars & Cumulative Curves (individual and total) |  | P | P | P
| Early and late Remaining units and costs, planned, actual, availability, overallocation |  | P | P | P
| Sight Lines |  | P | P | P | Configurable in P6
Team Usage / Analysis
| Display usage in daily timescale | P
---- more to follow -----
Activity Usage / Assignments Sheet
| Activity Usage Histogram in Activities view |  | P | P | P | OPC only shows activity usage aggregated to the project level.
| Activity Usage Spreadsheet in Activities view |  | P | P |  | On longer term OPC roadmap.
Costs - Bottom Up
| Actual Costs | P | P | P | P
| Actual Costs - Current Period | P | P | P | P
| Overtime Costs |  | P | P
---- more to follow -----
Top Down Cost Planning & Funds
Budgeting | [5 empty] | OPC supports Top-Down budgeting from the portfolio to the program to the project. At the project level, budgets can be defined and budget lines assigned to CBS codes. In P6, top down budgeting can be done at the EPS, Project, and WBS levels. While both products support top-down budgeting, the functionality is different and the data is not transferable between the products.
| Define Total Budget | P | P | P | P
| Import Budget from Excel |  |  |  | P
| Define Budget Line Item Records |  |  |  | P | Includes quantities, rates, hours, production rate, costs, categories and codes
| Approval Workflow |  |  |  | P
| Budget Changes | P | P | P | P
| Budget Transfers (between codes) |  |  |  | P
| Workflow for changes and transfer approvals |  |  |  | P
Cost sheet
| Define/Manage CBS Cost Structure |  |  |  | P | Workspace, Program and Project Cost Sheets
| Configurable Cost Sheet & Saved Views |  |  |  | P
| Drill down to Transactions |  |  |  | P
| View costs by CBS, cost category, or project |  |  |  | P
| Recalculate Cost Sheet rollups |  |  |  | P
Cashflow
| Planned Cashflow/spending plan | P | P | P | P | Note this is top down Planned budget for comparison with costed schedule
| Forecast Cashflow |  |  |  | P | Note this is top down Planned budget for comparison with costed schedule
| Benefit Plan | P | P | P | P
| Calculate Periodic Values using Curve Profiles |  |  |  | P
| Calcxulate Financials (NPV, ROI, etc) |  |  |  | P | NPV, Payback Period, IRR, ROI
| Other Cost Calculations |  |  |  | P | Extensive formula based UDF's supported other calculations required.
| Stored Snapshots and Comparison |  |  |  | P
| Capital and Expense cost curve breakdowns |  |  |  | P
Actuals
| Manually add actuals (lump sum or quantity based) |  |  |  | P
| Import actuals from Excel |  |  |  | P
| Approvals and workflows |  |  |  | P
| Consume funding sources with actuals |  |  |  | P
Project funds | [5 empty] | While both P6 and OPC support funding, the capabilities in OPC are much broader. In OPC, funding sources can be defined at the worspace, portfolio, or project level, and fund totals can be distributed from higher levels down to projects. Fund consumption can be tracked at any level. Due to the differences in capabilities between the products, this data is not transferable between products.
| Allocate/assign funds to project | P | P | P | P | Funds global in P6. In OPC, can live at WS, portfolio, program, or project.
| Define project-specific funds |  |  |  | P
| Consume funds |  |  |  | P | OPC tracks how much of a fund's totals have been consumed by a project.
| Import funds from Excel |  |  |  | P
| Manually edit time-phased fund distributions |  |  |  | P
Risks
| Manage/View Risks | P |  | P | P
| Configurable Risk Register, Saved Views |  |  |  | P
| Response Plans | P |  |  | P
| Hierarchical Responses with probability and impacts | P
| Cause/Effect/Notes | P |  | P | P
| Assign Configurable Proabability and Impact Matrix e.g. 3x3, 5x5 | P |  |  | P
| User Define Threshold e.g. Proximity |  |  |  | P
| Pre & Post Response Thresholds |  |  |  | Uniform, Triangle, Single Point
| Summary Chart | P | P | P | P
| Monte Carlo Risk Analysis |  |  |  | P | Pre & Post Response in one plan, Convergence, Removal Impact Analysis
| Apply Activity Uncertainty Calculations (all activities or selected activities) |  |  |  | P
| Weather Risks |  |  |  | P
| Monte Carlo Iteration Analysis |  |  |  | P
| Project-specific Risk Matrix |  |  |  | P
| Risk Codes | P |  |  | P
| Configured Fields | P | P | P | P | Greater functionality with codes and formula based UDF's in Primavera Cloud
| Distribution Results |  |  |  | P | Graphic (Dates, Costs, Duration) & Results Table, Pre & Post Response
| Mean Impact Tornado Charts |  |  |  | P | Activity or Risk Delay/Cost, Pre and Post Response
| Risk Removal Impact Tornado Charts |  |  |  | P | Cost, Date, Pre & Post Response
| Risk Workflows |  |  |  | P
| Run Standard Risk Reports | P |  |  | P | Reportwriter & BIP
| Discussions |  |  |  | P
Issues | [5 empty] | Custom Logs can be used for issue tracking in OPC.
| Manage/View Issues | P | P | P
| Issue Forms | P
Custom Logs
| Apply Templates |  |  |  | P | e.g. Lessons Learned Template, Quality Control Sets
| Configurable Views |  |  |  | P
| Files/documents/attachments/view and markups |  |  |  | P
| Import from Excel |  |  |  | P
| Discussions |  |  |  | P
Documents/Files
| Assign documents directly to activities | P |  |  | P
| Project File Repository from Template Folders/Docs |  |  |  | P
| Manage/View Project Documents | P |  |  | P
| Manage/View WPs & Docs | P | P | P | P
| Discussion threads on documents/files |  |  |  | P
| Document Reviews | P
| View any docs, markup tools, annotations, discussions |  |  |  | P
| File based permissions |  |  |  | P
| Document codes and other neta data |  |  |  | P
General Features
| Monitor Thresholds |  | P | P
| Claim Digger/Schedule Comparison |  | P | P | P
| Publish Project Website |  | P | P
| External Applications |  | P | P
| Store Period Performance |  | P | P | P
| Project Alerts |  |  |  | P
| Project-specific codes and calendars | P |  | P | P
| News Feed |  |  |  | P
| Top Down Estimation |  | P | P
Project Integration/Synchronisation
| Schedule Synchronisations | P |  |  | P | P6 relies on Gateway, Primavera Cloud presents in app end user functionality
| Monitor Synchronisations | P |  |  | P | P6 relies on Gateway, Primavera Cloud presents in app end user functionality
| P6 XML Import/Export (including baselines) | P | P | P | P
| MSP XML Import/Export | P | P | P | P
| MSP MPX Import/Export |  | P | P
| XER Import/Export |  |  | P |  | Planned for 2022 in OPC.
| IPMDAR Export | P | P | P
| UNCEFACT Export | P | P | P
| SDEF |  | P | P

## Resources
Resources
Feature | Detail | P6 EPPM Web Functionality | P6 EPPM Client Functionality | P6 Professional Functionality | Primavera Cloud | Notes
Administration
| Resources | P | P | P | P
| Resource Team | P
| Roles | P | P | P | P
| Role Teams | P
| Import/Export Resources & Roles | P | P | P | P
| Define Resource Shifts |  | P | P
| High Level Resource Planning | P | Can view Assignments |  | P
Assignment View
| Editable Assignment View | P | P | P |  | Assignment view exists in OPC; editing planned for 2022.
| Rename Columns | P | P | P | P
| Multiple Column Sorting | P | P | P | P
| Assignment Gantt | P |  |  |  | On OPC roadmap for 2022.
| Future Period Bucket Planning | P | P | P |  | On OPC roadmap.
Analysis
| Role Usage | P |  |  | P
| Resource Usage | P |  |  | P
| Resource Analysis | P |  |  | P
| Display usage in daily timescale | P |  |  | P

## Reports
Reports
Feature |  | P6 EPPM Web Functionality | P6 EPPM Client Functionality | P6 Professional Functionality | Primavera Cloud | Notes
Custom Reporting
| Create/Manage/View BI Publisher Reports | P |  |  | P
| Combined tabular/graphical reports | P |  |  | P
| Word or Excel Templates | P |  |  | P
| Integrated User Parameters at Run time | P |  |  | P
| Output Formats |  |  |  | PDF, XML, XLS, HTML, RTF
| Report on historical data |  |  |  | P
Report Writer
| User based Report Writer for Tabular Reports |  | P | P | P
| Save to Standard Reports for other users |  | P | P | P
Visualizer
| Custom Gantt Chart Reporting |  | P | P |  | Visualizer can be accessed from within P6 Pro or launched independently while using P6 Web.
| Timescaled Logic Diagrams |  | P | P
Custom Report Builder |  |  | P | P | P
Batch Reports |  | P | P | P |  | P6 Web has batch reporting for BI Publisher reports. P6 Pro has batch reporting for custom report builder
Report Register
| History of reports run with historical, viewable content |  |  |  | P
| Configurable Register of Reports |  |  |  | P
| Report Templates per Workspace |  |  |  | P
| Configurable Codes for Reports |  |  |  | P
| Print Layouts (Single Record Forms/Reports) |  |  |  | P
| Accessible within each App e.g. Task reports run from Task app |  |  |  | P

## Dashboards
Dashboards
Feature | Sub Feature | P6 EPPM Web Functionality | P6 EPPM Client Functionality | P6 Professional Functionality | Primavera Cloud | Notes
Dashboards | [5 empty] | This capability is delivered very differently between P6 EPPM and Primavera Cloud. The latter provides more capability to configure your own charts for Workspaces, Portfolios, Programs and Projects for all data areas, and augments that with standard tiles to include. P6 provides more out of the box graphs and views to include in a dashboard.
| Manage Dashboards | P |  |  | P
| Dashboards | Enterprise, Portfolios |  | Enterprise, Portfolios | Workspace, Portfolios, Program, Project
| Create Charts | P |  |  | P | More extensive custom chart creation in Prim Cloud
| Portfolio Views | P |  |  | P
| Schedule Performance | P
| Earned Value Performance | P
| Index Performance | P
| Project Statistics | P |  |  | P
| Project Health | P |  |  | P
| Project Notebooks | P
| Project Gantt Chart | P |  |  | P
| Document Reviews | P |  |  | NA | Handled through workflows and user notifications
| Open Requests for Resources | P
| Resource Analysis Chart | P |  |  | P
| My Projects | P |  |  | P | Provided in Primavera Cloud through a combination of projects tile and View All Projects scorecard
| My Workgroups | P |  |  | P | Provided in Primavera Cloud through a combination of workspaces tile and View All Workspaces scorecard
| My Activities | P |  |  | P | Provided in Primavera Cloud through My Activities app in User Home space.
| My Risks | P
| My Issues | P
| Communication Center | P
| My Documents | P
| My Calendar | P
| Custom Portlets | P |  |  | P
| Add Photos & Text |  |  |  | P
| Strategies Scorecard |  |  |  | P
| Trend / History Data |  |  |  | P
| Measures |  |  |  | P
| Top 10 Risks |  |  |  | P
| Top 10 Activities |  |  |  | P
| Top 10 Activities Starting this Week |  |  |  | P
| Top !0 Activities Finishing this Week |  |  |  | P
…. Etc …
| Geo Location Mapping & Reporting | P |  |  | P | P6 allows for tagging of co-ordinates whereas Primavera Cloud shows objects on a map across the application.

## Administration
Administration
Feature | Detail | P6 EPPM Web Functionality | P6 EPPM Client Functionality | P6 Professional Functionality | Primavera Cloud | Notes
Application Settings |  | P |  | Admin Preferences | P
Embedded enablement within application |  |  |  |  | P
UPK Enabled |  | P
Enterprise Data / Dictionaries | [5 empty] | Note : In Primavera Cloud, these dictionaries are defined per workspace and cascade down as required i.e. different departments or workspaces can have their own codes, udf', templates, rules per department and the projects within them.
| Currencies | P |  | P | P | Per Workspace in Primavera Cloud
| Timephased Exchange Rates |  |  |  | P | Per Workspace in Primavera Cloud
| Financial Periods/Reporting Cycles | P |  | P | P | Assumes 12 periods in Primavera Cloud. Define start month and day of each period. P6 periods are more configurable. On OPC roadmap to provide more configuration options. Until that happens, financial periods and associated data are not transferable between the products.
| Global Calendars | P | P | P | P | Per Workspace in Primavera Cloud
| Locations | P |  |  | P | Applied across more objects in Primavera Cloud with Geographic maps used to show locations of objects. In Primavera P6 it is effectively just a Lat/Long value.
| Overhead Codes | P |  |  | P | In OPC Hour Types are roughly the equivalent of Overhead Codes.
| Timesheet Periods | P |  | P |  | Timesheet Periods not as flexible in OPC. On roadmap to provide more flexibility. Until that happens, Timesheet data is not transferable between the products.
| Baseline Types | P |  | P |  | On OPC roadmap.
| Funding Sources | P | P | P | P | Funding Sources defined in the Funds app within each Workspace. Can be defined at workspace, portfolio, or project level in OPC. Data not transferable between products due to functional differences.
| Fund Source Codes |  |  |  | P | Also per Workspace in Primavera Cloud
| Fund Source UDF's |  |  |  | P | Also per Workspace in Primavera Cloud and Formulas
| Notebook Topics | P |  | P |  | On roadmap for 2022.
| Custom Logs |  |  |  | P | Typically used to define template registers for recording multiple records against the project, such as Lessons Learned Log.
| Custom Log Types |  |  |  | P | Also per Workspace in Primavera Cloud
| Custom Log Codes |  |  |  | P | Also per Workspace in Primavera Cloud
| Custom Log UDF's |  |  |  | P | Also per Workspace in Primavera Cloud
| Project Calendars | P | P | P | P
| Project Codes | P | P | P | P | Also per Workspace in Primavera Cloud
| Project UDFs | P | P | P | P | Also per Workspace in Primavera Cloud and Formulas
| WBS Codes |  |  |  | P
| WBS Categories | P |  | P |  | WBS Codes or UDFs can be used for this in OPC.
| WBS UDFs | P | P | P | P | Also per Workspace in Primavera Cloud
| Activity Codes - EPS | P | P | P | P | Also per Workspace in Primavera Cloud
| Activity Codes - Global | P | P | P | P | Also per Workspace in Primavera Cloud
| Activity Codes - Project | P | P | P | P
| Activity UDFs | P | P | P | P | Also per Workspace in Primavera Cloud and Formulas
| Cost Accounts | P | P | P |  | The CBS can be used in OPC.
| CBS - Cost Structure |  |  |  | P | Template CBS per workspace
| Cost Code Segments |  |  |  | P | Also per Workspace in Primavera Cloud
| Expense Categories | P |  | P
| Cost Categories |  |  |  | P | Also per Workspace in Primavera Cloud
| Expense UDFs | P | P | P
| Step Templates | P | P | P
| Step UDFs | P | P | P
| Task Codes |  |  |  | P | Also per Workspace in Primavera Cloud
| Task UDF's |  |  |  | P | Also per Workspace in Primavera Cloud
| Assignment UDFs | P | P | P | P | Also per Workspace in Primavera Cloud and Formulas
| Assignment Codes | P
| Rate Types | P |  | P | P | Delivered with costs in 20.8. Not a separate dictionary in OPC.
| Resource Dictionary | P | P | P | P | Also per Workspace in Primavera Cloud
| Resource Calendars | P | P | P | P | For Primavera Cloud, a specific calendar can be assigned to the resource, but it comes from the workspace list of calendars.
| Resource Shifts |  | P | P
| Resource Codes | P | P | P | P | Also per Workspace in Primavera Cloud
| Resource Curves | P | P | P
| Curve Profiles |  |  |  | P | Curve profiles are applied to other records in Primavera Cloud, not just resource assignments.
| Resource UDFs | P | P | P |  | On roadmap for 2022.
| Role Dictionary | P | P | P | P | Also per Workspace in Primavera Cloud
| Role Codes |  |  |  | P | Also per Workspace in Primavera Cloud
| Units of Measure | P |  | P | P | Also per Workspace in Primavera Cloud
| Risk Categories | P |  | P
| Risk Codes |  |  |  | P | Also per Workspace in Primavera Cloud
| Risk Matrix Templates | P |  |  | P | Also per Workspace in Primavera Cloud
| Risk Threshold Templates | P |  |  | P | Also per Workspace in Primavera Cloud
| Risk UDFs | P |  | P | P | Also per Workspace in Primavera Cloud and Formulas
| Risk Workflows |  |  |  | P | Also per Workspace in Primavera Cloud
| Risk Forms |  |  |  | P | Also per Workspace in Primavera Cloud
| Issue Codes | P
| Issue UDFs | P | P | P
| Document Categories | P |  | P
| Document Codes |  |  |  | P | Also per Workspace in Primavera Cloud
| Document Statuses | P |  | P
| Document UDFs | P |  |  | P | Also per Workspace in Primavera Cloud
| WP & Docs UDFs |  | P | P
| Work Package Codes |  |  |  | P | Also per Workspace in Primavera Cloud
| Work Package UDF's |  |  |  | P | Also per Workspace in Primavera Cloud
Global Change - Update existing fields |  | P | P | P | P | Global change for Activities delivered in 20.4, resource assignments are on the backlog, additional date field updates are also on the backlog. Global Change is per project in OPC.
Global Change - Update existing fields - WBS level fields |  | P
Global Change - Perform calculations |  |  | P | P
Global Schedule Services |  | P |  |  | P | Manage Services in OPC.
User Access
| Users | P |  | P | P
| User Groups |  |  |  | P
| OBS | P | P | P |  | Not needed in OPC.
| Global Security Profiles | P |  | P | P | Global and Workspace Permission Sets in OPC.
| Project Security Profiles | P |  | P | P | Project Permission Set in OPC.
| Companies |  |  |  | P
User Interface Views
| Manage Content | P |  |  | P | Admin can show/hide apps for specific users in OPC.
| Activity Editing Settings | P

## Ideas
Administration
Feature | Detail | P6 EPPM Web Functionality | P6 EPPM Client Functionality | P6 Professional Functionality | Primavera Cloud | Notes
Ideas
| Scorecard for Ranking & Comparison |  |  |  | P
| Configured Views for Scorecards |  |  |  | P
| Evaluation Matrix & Configured Scoring |  |  |  | P
| Configurable Forms & Workflow |  |  |  | P
| Configured Fields |  |  |  | P
| Configrued Codes |  |  |  | P
| Auto creation of Proposals or Projects |  |  |  | P
| Investor Map |  |  |  | P
| File Repository per Idea |  |  |  | P